Please enter your name as it appears in Blackboard.
Please enter 2 or 3 capital letters that will represent you in the "Assigned To" column on each Sprint Backlog tab of this spreadsheet.
Please enter your UTA student ID number.
Select the sprint number (1, 2, etc.) in which you plan to implement this feature. This is just for planning purposes, it won't affect your grade.

In Scrum, you only plan the current sprint, not future sprints, so you don't need to fill this in for any features not planned for the current sprint.

If you planned a "full credit" feature for the current sprint but don't complete it, then just update this cell for the next sprint. This will only affect your grade if this feature was *required* to be completed by a specific sprint, and is not.

If you planned a "bonus" or "extreme bonus" feature for the current sprint but don't complete it, and you don't want to use it for the next sprint, just use the Delete key to leave this cell blank. Your "full credit" grade will not be penalized for this decision.
This cell may only contain a valid sprint number - an integer between 1 and the number of sprints in the project. Or it may be left blank (hint: use the Delete key).
Leave blank initially (hint: Use the Delete key)
Select "In Work" when you begin designing and coding this feature.
Select "In Test" when this feature is fully coded and you are testing it.
Select Finished ONLY when the feature works well and is READY TO SHIP.
   "Finished in Sprint 1" means it was delivered at the end of Sprint 1.
   "Finished in Sprint 2" / "Finished in Sprint 3" are the same for those sprints.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
The list contains the Feature IDs from the same column on the Product Backlog tab.

For each (ahem) Feature ID, create one or more rows in this table representing the tasks you need to complete to implement that feature.

For example, for a "Provide Help to User" feature, you might assign a Feature ID of "HELP" on the Product Backlog. Then, in the Sprint Backlog table, you might have 3 rows of tasks with Feature ID of Help - "Write help text", "Create help class to display help", and "Update CLI to accept '?' command".

COPY the status cell from row 1 for each row that you add, so that you can select its status with a drop-down. This will ensure that the Sprint Burn Chart at the top updates itself automatically as you complete your tasks.
Leave blank until task is begun.
Select "In Work" when started (for long tasks only).
Select Completed ONLY when this task is done.
   Select "Completed Day 1" if finished on the first day, and
   similarly for "Completed on Day 2" et. al.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
The list contains the Feature IDs from the same column on the Product Backlog tab.

For each (ahem) Feature ID, create one or more rows in this table representing the tasks you need to complete to implement that feature.

For example, for a "Provide Help to User" feature, you might assign a Feature ID of "HELP" on the Product Backlog. Then, in the Sprint Backlog table, you might have 3 rows of tasks with Feature ID of Help - "Write help text", "Create help class to display help", and "Update CLI to accept '?' command".

COPY the status cell from row 1 for each row that you add, so that you can select its status with a drop-down. This will ensure that the Sprint Burn Chart at the top updates itself automatically as you complete your tasks.
## Product Backlog
Product Name:	C1325 Library Management System					Complete Fields in Green!!!
Team ID:

Name:	Chris Jakins
Initials:	CFJ
Student ID:	1000802309

Teaming is not available for this assignment!
Optional teaming may be available in future assignments

	Remaining	Completed (this sprint)
Total Features	19		Total
Sprint 1 Left	12	7	1
Sprint 2 Left	5	7	2
Sprint 3 Left	3	2	3

				Note: Priority of unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
				Additional features may be proposed by the student but must be approved by the Product Owner in writing
			Sprints
Feature ID	Priority		Planned	Status	As a...	I want to...	So that...	Notes
AP	1		1	Finished in Sprint 1	Librarian	Add a publication	I can keep track of what is in the library
LP	2		1	Finished in Sprint 1	Librarian	List all publications	I can find out what is in the library	This will also be needed for the next two features
CO	3		1	Finished in Sprint 1	Librarian	Check out a publication	I can track who has borrowed each publication	Each publication will need to know if it is checked out or not
CI	4		1	Finished in Sprint 1	Librarian	Check in a publication	I can tell when a publication is returned
HE	5		1	Finished in Sprint 1	Librarian	Get help	I can learn how to use the system
PA	6		1	Finished in Sprint 1	Librarian	Add a patron	I can conveniently keep track of all patrons	This is the Bonus level for Sprint #1
SP	7		1	Finished in Sprint 1	Librarian	Select a patron when checking out a pub	I don't have to rekey recurring patron info	This is the Bonus level for Sprint #1
DMM	8		2	Finished in Sprint 2	Librarian	Use a standard dialog for the main menu	I can interact more naturally with the system
DNP	9		2	Finished in Sprint 2	Librarian	Use a series of dialogs for a new publication	I can interact more naturally with the system
DLP	10		2	Finished in Sprint 2	Librarian	Use a stand dialog for the list of publications	I can interact more naturally with the system
DH	11		2	Finished in Sprint 2	Librarian	Use dialogs for all other interaction (e.g., help)	I can interact more naturally with the system
DCO	12		2	Finished in Sprint 2	Librarian	Use dialogs for check in and check out	I can interact more naturally with the system
DRM	13		2	Finished in Sprint 2	Librarian	Add rich text to the main menu (dialog)	The menu is easier to navigate	This is the Bonus level for Sprint #2
DRH	14		2	Finished in Sprint 2	Librarian	Add rich text to the help dialog	The help text is easier to understand	This is the Bonus level for Sprint #2
DCP	15		2	Finished in Sprint 3	Librarian	Use a custom dialog to create new pubs	I can create them more quickly	This is the Extreme Bonus level for Sprint #2
MW	16		3	Finished in Sprint 3	Librarian	Interact with a main window with drop-down menus	I can interact more naturally with the system	Replace the main menu dialog with a main window that is always visible
MT	17		3		Librarian	Add a toolbar to the main menu	I can more quickly access common features	This is the Bonus level for Sprint #3
MP	18		3		Librarian	Add a scrolling publications table to main window	I can more quickly look up publications	This is the Extreme Bonus level for Sprint #3
CU	19		1		Librarian	Add custom info for each publication type	I can keep better track of library assets	This is the Extreme Bonus level for Sprint #1
Product Backlog Burn Chart
Sprints
Features Remaining at Start of Sprint

## Sprint 01 Backlog
Sprint #	1		Complete Fields in Green!!!
Start on	Sep 21		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Sep 28
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	19
Day 1 Left	19	0
Day 2 Left	8	11
Day 3 Left	5	3
Day 4 Left	5	0
Day 5 Left	5	0
Day 6 Left	5	0
Day 7 Left	0	5

	Feature ID		Description	Status	Notes
	AP		Create a Publication class with data and a constructor	Completed Day 2	Included a WRITTEN test with each constructor and method!
	AP		Add the to_string method to Publication	Completed Day 2
	CO		Add the is_checked_out method to Publication	Completed Day 2
	CO		Add the check_out method to Publication	Completed Day 2
	CI		Add the check_in method to Publication	Completed Day 2
	LP		Create a Library class with data	Completed Day 2
	AP		Add the add_publication method to Library	Completed Day 2
	LP		Add the publication_to_string method to Library	Completed Day 2
	LP		Add the number_of_publications method to Library	Completed Day 2
	CO		Add the check_out method to Library	Completed Day 2
	CI		Add the check_in method to Library	Completed Day 2
	HE		Create main with ‘View’	Completed Day 3
	HE		Add help functionality	Completed Day 3
	HE		Add secret option to populate library	Completed Day 3
	PA		Create Patron Class	Completed Day 7
	PA		Implement to_string	Completed Day 7
	PA		Update main	Completed Day 7
	PA		Update Library and Publication class	Completed Day 7
	SP		Change checkout function in main	Completed Day 7
Sprint Burn Chart
Tasks
Days

## Sprint 02 Backlog
Sprint #	2		Complete Fields in Green!!!
Start on	Sep 28		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Oct 05
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	12
Day 1 Left	12	0
Day 2 Left	12	0
Day 3 Left	12	0
Day 4 Left	7	5
Day 5 Left	0	7
Day 6 Left	0	0
Day 7 Left	0	0

	Feature ID		Description	Status	Notes
	DMM		Import the Dialog class	Completed Day 4	Included a WRITTEN test with each constructor and method!
	DMM		Update main menu to utilize a dialog	Completed Day 4
	DMM		Clean up rest of code interacting with main menu	Completed Day 4
	DNP		Change add publication method to use dialog	Completed Day 4
	DNP		Incorporate Genre, Media, and Target Age into final result	Completed Day 4
	DLP		Change list publication method to use dialog	Completed Day 5
	DH		Change help message to use dialog	Completed Day 5
	DCO		Change patron functionality to use dialog	Completed Day 5
	DCO		Change check out to use dialog	Completed Day 5
	DCO		Change check in to use dialog	Completed Day 5
	DRM		Make the main menu look fancy!	Completed Day 5
	DRH		Make the help screen look even more helpful!	Completed Day 5
	DCP
Sprint Burn Chart
Tasks
Days

## Sprint 03 Backlog
Sprint #	3		Complete Fields in Green!!!
Start on	Oct 05		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Oct 12
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	4
Day 1 Left	4	0
Day 2 Left	3	1
Day 3 Left	0	3
Day 4 Left	0	0
Day 5 Left	0	0
Day 6 Left	0	0
Day 7 Left	0	0

	Feature ID		Description	Status	Notes
	MW		Move main window class over	Completed Day 2	Included a WRITTEN test with each constructor and method!
	MW		Update main window class to implement dialogs	Completed Day 3
	MW		Change add publication dialog to have one main dialog	Completed Day 3
	MW		Fix bugs with check in and check out regarding cancel case	Completed Day 3
	MT
	MP
Sprint Burn Chart
Tasks
Days